## Backend
SL No | Live Url | Screen | API Name | Method | Request parameters | Success Response | Normal Failed Response | Working Status | Note
1 | http://localhost:8000/api/user/login | Login | api/user/login | POST | { "email": "rita5@gmail.com", "password" : "12345678" } | { "success": "1", "message": "login successfully", "result": { "access_token": "ymp1fg8TImlnXPv6vsTFJERMtpaFDSYBmtlvbZBc", "token_type": "Bearer" } } } |  | Done
2 | http://localhost:8000/api/user/register | registration | api/user/register | POST | { "name" : "chira", "email" : "kk@gmail.com", "password" : "12345678" } | { "success": "1", "message": "registration Sucessfully", "result": { "access_token": "HSsvSsf5rfEqP4fWvVa8Agma8j9Yw0GpxJaRbwg6", "token_type": "Bearer" } } |  | Done
3 | http://localhost:8000/api/user/me | user details | api/user/me | GET | Authorization-bearer token | { "success": "1", "message": "sucessfully fetch", "result": { "id": 19, "name": "Hardik57826 Savani", "email": "rita5@gmail.com", "email_verified_at": null, "created_at": "2022-03-28T17:57:05.000000Z", "updated_at": "2022-03-28T17:57:05.000000Z" } } |  | Done
4 | http://localhost:8000/api/team/addcapture | add capture | api/team/addcapture | POST | formdata param -nameAuthorization-bearer token | { "status": 1, "message": "Capture Added." } |  | Done
5 | http://localhost:8000/api/team/editcapture | edit capture | api/team/editcapture | POST | formdata param -id,nameAuthorization-bearer token | {"status":1,"message":"Capture Updated."} |  | Done
6 | http://localhost:8000/api/team/deletecapture/id | Delete capture | api/team/deletecapture/1 | GET | Authorization-bearer token | { "status": 1, "success": "capture deleted succcessfully" } |  | Done
7 | http://localhost:8000/api/team/getcapture | fetch capture | api/team/getcapture | GET | Authorization-bearer token | "status": 1, "message": "Success", "result": [ { "id": 2, "name": "test99", "created_at": "2022-03-24T08:23:23.000000Z", "updated_at": "2022-03-24T10:25:59.000000Z" }, { "id": 3, "name": "test68", "created_at": "2022-03-24T10:32:33.000000Z", "updated_at": "2022-03-29T08:50:10.000000Z" } ] } |  | Done
8 | http://localhost:8000/api/team/addstaff | add staff | api/team/addstaff | POST | Authorization-bearer token, staff-parameter | {"status":1,"success":"Added Staff"} |  | Done
9 | http://localhost:8000/api/team/getstaff | fetch staff | api/team/getstaff | GET | Authorization-bearer token | { "status": 1, "message": "Success", "result": [ { "id": 1, "staff": "50", "created_at": "2022-03-24T13:32:08.000000Z", "updated_at": "2022-03-24T13:32:08.000000Z" }, } |  | Done
10 | http://localhost:8000/api/team/staffdelete/id | delete staff | api/team/staffdelete/5 | GET | bearrer token | {"status":1,"success":"Staff deleted succcessfully"} |  | Done | This is not needed .
11 | http://localhost:8000/api/team/editstaff | edit staff | api/team/editstaff | POST | parameter -id,staff Authorization-bearer token | { "status": 1, "message": "Staff Updated." } |  | Done
12 | http://localhost:8000/api/team/adddepartment | add department | api/team/adddepartment | POST | parameter -department Authorization-bearer token | {"status":1,"success":"Added Department"} |  | Done
13 | http://localhost:8000/api/team/editdepartment | edit department | api/team/editdepartment | POST | parameter -id,departmentAuthorization-bearer token | { "status": 1, "message": "Department Updated." } |  | Done | region list api will need for App
14 | http://localhost:8000/api/team/getdepartment | fetch department | api/team/getdepartment | GET |  | "status": 1, "message": "Success", "result": [ { "id": 1, "department": "Hospilaity", "created_at": "2022-03-24T11:16:53.000000Z", "updated_at": "2022-03-29T12:08:54.000000Z" }, ] } |  | Done
15 | http://localhost:8000/api/team/departmentdelete/{id} Delete Department | delete department | api/team/departmentdelete/4 | GET |  | { "status": 1, "success": "Department deleted succcessfully" } |  | Done
16 | localhost:8000/api/team/addteam | Add team | api/team/addteam | POST | parameter-teamname,phoneno,captchaid,deptid,Staffid | { "status": 1, "message": "Team Added." } |  | Done
17 | http://localhost:8000/api/team/fetchteam | Fetch Team | api/team/fetchteam | GET |  | { "status": 1, "message": "Success", "result": [ { "dept": { "id": 3, "teamname": "testd", "phoneno": "9433722030", "staffid": 4, "captchaid": "\"[3,4]\"", "deptid": 2, "created_at": "2022-03-23T12:40:35.000000Z", "updated_at": "2022-03-25T12:37:09.000000Z", "created_by": 7, "dept": { "id": 2, "department": "food & beverage", "created_at": "2022-03-24T11:43:31.000000Z", "updated_at": "2022-03-24T12:04:39.000000Z" }, "staff": { "id": 4, "staff": "20-50", "created_at": "2022-03-25T07:14:39.000000Z", "updated_at": "2022-03-25T07:44:38.000000Z" }, "createdby": { "id": 7, "name": "Hardik57 Savani", "email": "admin67@gmail.com", "email_verified_at": null, "created_at": "2022-03-23T06:36:21.000000Z", "updated_at": "2022-03-23T06:36:21.000000Z" } }, "captcha": [ "test68" ] }, { "dept": { "id": 9, "teamname": "test58795", "phoneno": "8334927302", "staffid": 5, "captchaid": "\"[2 ,3]\"", "deptid": 4, "created_at": "2022-03-29T09:16:16.000000Z", "updated_at": "2022-03-29T09:16:16.000000Z", "created_by": 19, "dept": null, "staff": null, "createdby": { "id": 19, "name": "Hardik57826 Savani", "email": "rita5@gmail.com", "email_verified_at": null, "created_at": "2022-03-28T17:57:05.000000Z", "updated_at": "2022-03-28T17:57:05.000000Z" } }, "captcha": [ "test99", "test68" ] }, { "dept": { "id": 10, "teamname": "test587958", "phoneno": "8334927302", "staffid": 4, "captchaid": "\"[2 ,3]\"", "deptid": 2, |  | Done
18 | localhost:8000/api/team/editteam | edit team | api/team/editteam | POST | parameter -id,teamname,staffid,captchaid,deptid,Authorization-bearrer token | { "status": 1, "message": "Team Updated." } |  | Done
19 | http://localhost:8000/api/team/deleteteam/8 | deleteam | api/team/deleteteam/8 | GET | Authorization-bearer token | { "status": 1, "success": "Team deleted succcessfully" } |  | Done
20 | http://localhost:8000/api/team/addteammembers | add teammember | api/team/addteammembersPOST | POST | Authorization -bearer token parameter-team_id,user_id | {"status":1,"message":"Teammember Added."} |  | Done
21 | http://localhost:8000/api/team/fetchteammembers | update teammember | api/team/fetchteammembers | GET | {"status":1} | { "status": 1, "message": "Success", "result": [ { "team": { "id": 1, "user_id": 2, "team_id": 3, "created_at": "2022-03-23T14:17:41.000000Z", "updated_at": "2022-03-25T13:39:39.000000Z", "users": { "id": 2, "name": "chira", "email": "mail2chirashree@gmail.com", "email_verified_at": null, "created_at": "2022-03-21T14:44:44.000000Z", "updated_at": "2022-03-21T14:44:44.000000Z" }, "teams": { "id": 3, "teamname": "testd", "phoneno": "9433722030", "staffid": 4, "captchaid": "\"[3,4]\"", "deptid": 2, "created_at": "2022-03-23T12:40:35.000000Z", "updated_at": "2022-03-29T13:17:34.000000Z", "created_by": 19 } }, "dept": { "id": 2, "department": "food & beverage", "created_at": "2022-03-24T11:43:31.000000Z", "updated_at": "2022-03-24T12:04:39.000000Z" }, "captures": [ { "id": 3, "name": "test68", "created_at": "2022-03-24T10:32:33.000000Z", "updated_at": "2022-03-29T08:50:10.000000Z" }, null ], "staff": { "id": 4, "staff": "20-50", "created_at": "2022-03-25T07:14:39.000000Z", "updated_at": "2022-03-25T07:44:38.000000Z" }, "createdat": { "id": 19, "name": "Hardik57826 Savani", "email": "rita5@gmail.com", "email_verified_at": null, "created_at": "2022-03-28T17:57:05.000000Z", "updated_at": "2022-03-28T17:57:05.000000Z" } }, |  | Done | hospital list when user request with region . need api for app
22 | http://localhost:8000/api/team/editteammembers | edit teammembers | api/team/editteammembersPOST | POST | parameter,id,user_id,team_id,authorization-bearer token | { "status": 1, "message": "Teammember Updated." } |  | Done
23 | http://localhost:8000/api/team/deleteteammembers/id delete teammembers | Delete teammembers | api/team/deleteteammembers/4 GET bearer token |  |  | { "status": 1, "success": "Teammember deleted succcessfully" } |  | Done
24 | http://localhost:8000/api/team/addattendance | Add attendance | api/team/addattendance | POST | parameter-in_time,out_time,Authorization-bearer token,(user),parameter-in_time,out_time,employee_id,Authorization-bearer token,(user), | { "status": 0, "message": "error", "error": "User attandance Already exist" } |  | Done
25 | http://localhost:8000/api/team/deleteattendance/1 Delete attendance | delete attendance | api/team/deleteattendanceGET | GET | bearer_token | { "status": 1, "success": "attendance deleted succcessfully" } |  | Done
26 | http://localhost:8000/api/team/checkattendance | Check attendance | api/team/checkattendance(user) | GET | bearer_token | { "status": 1, "message": "Success", "result": [ { "id": 7, "employee_id": 19, "attendance_date": "2022-03-28", "in_time": "10.30 A.m", "out_time": "8.30p.m", "created_at": "2022-03-28T18:06:25.000000Z", "updated_at": "2022-03-28T18:06:25.000000Z", "users": { "id": 19, "name": "Hardik57826 Savani", "email": "rita5@gmail.com", "email_verified_at": null, "created_at": "2022-03-28T17:57:05.000000Z", "updated_at": "2022-03-28T17:57:05.000000Z" } }, { "id": 10, "employee_id": 19, "attendance_date": "2022-03-29", "in_time": "10.30 A.m", "out_time": "8.30p.m", "created_at": "2022-03-29T04:29:01.000000Z", "updated_at": "2022-03-29T04:29:01.000000Z", "users": { "id": 19, "name": "Hardik57826 Savani", "email": "rita5@gmail.com", "email_verified_at": null, "created_at": "2022-03-28T17:57:05.000000Z", "updated_at": "2022-03-28T17:57:05.000000Z" } } ] } |  | Done
27 | [7 empty] | Done | Language list api will need for app
28 | http://localhost:8000/api/team/editattendance | edit attendance | api/team/editattendance | POST | id,in_time,out_time-parameter(user) | {"status":1,"success":"Updated user attendance"} |  | Done
29 |  |  |  |  | id,in_time,out_time,employee_id-Admin |  |  | Done
30 | [7 empty] | Done
31 | http://localhost:8000/api/team/checkattendance | Check attendance | api/team/checkattendance | GET | bearer token | {"status":1,"message":"Success","result":[{,"attendance":[{"id":11,"employee_id":7,"attendance_date":"2022-03-30","in_time":" 10:30:45","out_time":" 8:40:35","created_at":"2022-03-30T12:07:18.000000Z","updated_at":"2022-03-30T12:07:18.000000Z","users":{"id":7,"name":"Hardik57 Savani","email":"admin67@gmail.com","email_verified_at":null,"created_at":"2022-03-23T06:36:21.000000Z","updated_at":"2022-03-23T06:36:21.000000Z"}}]}]} |  | Done
32 | http://localhost:8000/api/team/checkattendance | Check attendance | api/team/checkattendance GET |  | bearer token | {"status":1,"message":"Success","result":[{"attendance":[{"id":12,"employee_id":19,"attendance_date":"2022-03-30","in_time":"2020-07-19 07:39:45","out_time":"2020-07-19 07:51:07","created_at":"2022-03-30T13:31:40.000000Z","updated_at":"2022-03-30T13:31:40.000000Z","users":{"id":19,"name":"Hardik57826 Savani","email":"rita5@gmail.com","email_verified_at":null,"created_at":"2022-03-28T17:57:05.000000Z","updated_at":"2022-03-28T17:57:05.000000Z"}}]}]} |  | Done
33 | [7 empty] | Done
34 | http://localhost:8000/api/team/checkattendance | [6 empty] | Done
35 | localhost:8000/api/timesheet/start | Timesheet start | api/timesheet/start | POST | bearer token | {"success":"1","message":"Tracking started."} |  | Done
36 | localhost:8000/api/timesheet/stop | Timesheet stop | api/timesheet/stop | POST | bearer token | { "success": "1", "message": "Tracking stopped." } |  | Done
37 | http://localhost:8000/api/user/logout | Logout | api/user/logout | POST | bearer token | {"message":"successfully log out","success":"1"} |  | Done
38 | http://localhost:8000/api/team/singlecapture/{id} | Capture | api/team/singlecapture/2 | GET | bearer token | { "status": 1, "message": "Success", "result": [ { "id": 2, "name": "test99", "created_at": "2022-03-24T08:23:23.000000Z", "updated_at": "2022-03-24T10:25:59.000000Z" } ] } |  | Done
39 | http://localhost:8000/api/team/singlestaff/{id} | Staff | api/team/singlestaff/1 | GET | bearer token | { "status": 1, "message": "Success", "result": [ { "id": 1, "staff": "20-50", "created_at": "2022-03-24T13:32:08.000000Z", "updated_at": "2022-03-29T11:37:32.000000Z" } ] }
40 | http://localhost:8000/api/team/singledepartment/{id} Department |  | api/team/singledepartment/2 GET |  | bearer token | { "status": 1, "message": "Success", "result": [ { "id": 2, "department": "food & beverage", "created_at": "2022-03-24T11:43:31.000000Z", "updated_at": "2022-03-24T12:04:39.000000Z" } ] }
41 | http://localhost:8000/api/team/singlestaff/{id} | Staff | api/team/singlestaff/1 | GET | bearer token | { "status": 1, "message": "Success", "result": [ { "id": 1, "staff": "20-50", "created_at": "2022-03-24T13:32:08.000000Z", "updated_at": "2022-03-29T11:37:32.000000Z" } ] }
42 | http://localhost:8000/api/team/singleteam/{id} | team | api/team/singleteam/11 | GET | bearer token | { "status": 1, "message": "Success", "result": [ { "dept": { "id": 11, "teamname": "test58795878", "phoneno": "8334927302", "staffid": 4, "captchaid": "\"[2 ,3]\"", "deptid": 2, "created_at": "2022-03-29T12:58:56.000000Z", "updated_at": "2022-03-29T12:58:56.000000Z", "created_by": 19, "dept": { "id": 2, "department": "food & beverage", "created_at": "2022-03-24T11:43:31.000000Z", "updated_at": "2022-03-24T12:04:39.000000Z" }, "staff": { "id": 4, "staff": "20-50", "created_at": "2022-03-25T07:14:39.000000Z", "updated_at": "2022-03-25T07:44:38.000000Z" }, "createdby": { "id": 19, "name": "Hardik57826 Savani", "email": "rita5@gmail.com", "email_verified_at": null, "created_at": "2022-03-28T17:57:05.000000Z", "updated_at": "2022-03-28T17:57:05.000000Z" } }, "captcha": [ "test99", "test68" ] } ] }
43 | http://localhost:8000/api/team/singleteammembers/{id} teammember api/team/singleteammembers/2 |  |  | GET | bearer token | { "status": 1, "message": "Success", "result": [ { "team": { "id": 2, "user_id": 7, "team_id": 2, "created_at": "2022-03-24T05:16:26.000000Z", "updated_at": "2022-03-24T05:16:26.000000Z", "users": { "id": 7, "name": "Hardik57 Savani", "email": "admin67@gmail.com", "email_verified_at": null, "created_at": "2022-03-23T06:36:21.000000Z", "updated_at": "2022-03-23T06:36:21.000000Z" }, "teams": null }, "dept": [], "captures": [], "staff": [], "createdat": [] } ] }
44 | http://localhost:8000/api/team/singleattendance/{id} | Single attendance(Admin) | api/team/singleattendance/14 | GET | bearer token | { "status": 1, "message": "Success", "result": [ { "attendance": [ { "id": 14, "employee_id": 19, "attendance_date": "2022-03-31", "in_time": "2020-07-19 07:39:45", "out_time": "2020-07-19 07:51:07", "created_at": "2022-03-31T05:31:48.000000Z", "updated_at": "2022-03-31T05:31:48.000000Z", "users": { "id": 19, "name": "Hardik57826 Savani", "email": "rita5@gmail.com", "email_verified_at": null, "created_at": "2022-03-28T17:57:05.000000Z", "updated_at": "2022-03-28T17:57:05.000000Z" } } ] } ] }
45
46 | api/team/singleattendance/{id} | single attendance | api/team/singleattendance/14 | bearer token | { "status": 1, "message": "Success", "result": [ { "attendance": [ { "id": 14, "employee_id": 19, "attendance_date": "2022-03-31", "in_time": "2020-07-19 07:39:45", "out_time": "2020-07-19 07:51:07", "created_at": "2022-03-31T05:31:48.000000Z", "updated_at": "2022-03-31T05:31:48.000000Z", "users": { "id": 19, "name": "Hardik57826 Savani", "email": "rita5@gmail.com", "email_verified_at": null, "created_at": "2022-03-28T17:57:05.000000Z", "updated_at": "2022-03-28T17:57:05.000000Z" } } ] } ] }
47 | http://localhost:8000/api/user/singlefetchuser/1 | single fetch user | user/singlefetchuser/1 GET |  | bearer token | { "success": "1", "message": "sucessfully fetch", "result": { "id": 21, "name": "Hardik57826 Savani", "email": "rita58@gmail.com", "email_verified_at": null, "created_at": "2022-03-28T18:00:52.000000Z", "updated_at": "2022-03-28T18:00:52.000000Z", "permissions": [], "roles": [ { "id": 7, "name": "admin", "guard_name": "web", "created_at": "2022-03-28T18:00:52.000000Z", "updated_at": "2022-03-28T18:00:52.000000Z", "pivot": { "model_id": 21, "role_id": 7, "model_type": "App\\Models\\User" } } ] } }
49 | http://localhost:8000/api/user/editprofile | profile | api/user/editprofile | GET | bearer token | { "status": 1, "message": "User Updated." }
50 | localhost:8000/api/timesheet | timesheet | localhost:8000/api/timesheetGET |  | bearer token | { "status": "1", "message": "Success", "data": [ { "start": "2022-03-31T14:57:51.000000Z", "end": "2022-03-31T14:58:02.000000Z" } ] }

## App_Api (hidden)
SL NO | Live Url | Screen | API Name | Method | Request parameters | Success Response | Failed Response | Working Status | Note | Note
1 | http://deappdev.opapps.io/api/app-register | New user register | api/app-register | POST | { "name":"Smon", "email":"som@gmail.com", "user_type":"1", "country_id":"1", "hospital_id":"3", "password":"123456", "password_confirmation":"123456" } | { "status": 1, "messages": [ "You have successfully resgistered." ], "errors": [], "result": [ { "id": 12, "name": "Smon", "deapp_id": "23601P7269", "email": "som@gmail.com", "date": "15-Mar-2022" } ] } | { "status": 0, "messages": "Error", "errors": [ "The name field is required.", "The username has already been taken.", "The email has already been taken." ] } ----------------- { "status": 0, "messages": "Error", "errors": [ "The name field is required." ] } | Done |  | { "status": 1, "message": "You have successfully registered.", "result": { "id": 14, "name": "ramindra Das", "email": "ramindra@gmail.com", "username": "ramindra17", "status": 1, "date": "03-Mar-2022" } "errors": { "email": "." "Password" ,"" } } }
2 | http://deappdev.opapps.io/api/app-login | Login | api/app-login | POST | { "username":"ramindra17", "password":"123456" } | { "status": 1, "messages": [ "You have login successfully." ], "errors": [], "result": [ { "id": 7, "name": "jon", "email": "jon@gmail.com", "date": "04-Mar-2022", "token": "65¦0BCr94unZKtcMtE5oyeT3T2hqXxq18CMp4quJ9Sy" } ] } | { "status": 0, "messages": "Error", "errors": [ "Incorrect password, please check it and enter again!" ] } ------------ { "status": 0, "messages": "Error", "errors": [ "Username can not be blank!" ] } | Done
3 | http://deappdev.opapps.io/api/quick-links | Quick links | api/quick-links | GET |  | { "status": 1, "messages": [ "Success" ], "errors": [], "result": [ [ { "id": 18, "value": "useful_information", "label": "Useful Information", "quick_links": [ { "id": 43, "value": "sickday_rules", "label": "Sickday Rules", "url": "https://s3-us-east-1.amazonaws.com//618eb0c3edd7f_Patient-advice-for-sick-day.pdf", "type": { "id": 1, "value": "pdf", "label": "PDF" } }, { "id": 44, "value": "glucagonglucagen-_how_to_give_an_injection", "label": "Glucagon/Glucagen - How to give an injection", "url": "https://player.vimeo.com/external/207451449.sd.mp4?s=24d24db5337ecee2418822b20c4ffccbce464159&profile_id=165", "type": { "id": 3, "value": "video", "label": "Video" } }, { "id": 45, "value": "healmed_website", "label": "HEAL.med website", "url": "https://www.heal-med.co.uk", "type": { "id": 2, "value": "url", "label": "URL" } }, { "id": 46, "value": "ketone_sticker", "label": "Ketone Sticker", "url": "https://s3-us-east-1.amazonaws.com//61de6b2198fdf_Deapp-Ketone-Sticker.pdf", "type": { "id": 1, "value": "pdf", "label": "PDF" } } ] } ] ] } |  | Done
4 | http://deappdev.opapps.io/api/app-get-language | Get Languages List | api/app-get-language | GET |  | { "status": 1, "messages": [ "Success" ], "errors": [], "result": [ { "id": 3, "label": "Urdu", "status_id": 1, "date": "7-Mar-2022" }, { "id": 2, "label": "Hindi", "status_id": 1, "date": "7-Mar-2022" }, { "id": 1, "label": "English", "status_id": 1, "date": "7-Mar-2022" } ] } | { "status": 0, "messages": ["Error"], "errors": [ "No data found !" ] } | Done
5 | http://deappdev.opapps.io/api/app-get-hospitals | Get Hospitals | api/app-get-hospitals | POST | { "region_id":1 } | { "status": 1, "messages": "Success", "errors": [], "result": [ { "id": 2, "hospital_name": "AMRI" }, { "id": 3, "hospital_name": "Applo" } ] } | { "status": 0, "messages": [ "Error" ], "errors": [ "No data found !" ] } | Done
6 | http://deappdev.opapps.io/api/app-get-hospitals-details | Get Hospital Details | api/app-get-hospitals-details | POST | { "hospital_id":"2" } | { "status": 1, "messages": [ "Success" ], "errors": [], "result": [ { "id": 3, "hospital_name": "forties", "status_id": 1, "region_id": 1, "pz_code": "PZ236", "region_name": "England", "office_contact_weekdays": "8990890901", "dietitian_contact": "2345678901", "switchboard": "3456790234", "email_signoff": "forties2@gmail.com", "weight": 200, "out_of_hours_contact": "1234578902" } ] } | { "status": 0, "messages": [ "Error" ], "errors": [ "No data found." ] } | Done
7 | http://deappdev.opapps.io/api/app-get-sessions | Get Sessions Details | api/app-get-sessions | GET | { "language_id":"2" } This is for only language filter | { "status": 1, "messages": "Success", "errors": [], "result": [ { "sessions": [ { "session_id": 1, "session_name": "Introduction to the app", "order": 0, "steps": [ { "step_id": 1, "step_name": "Step 1", "step_type": "App\\Models\\Session\\Video", "videos": [ { "video_id": 1, "video_thumbnail": "1a9d169d6fe844543fa797ab1ac4easc.png", "languages": [ { "language_id": 1, "language_name": "English", "device": [ { "device_type": "tablet", "url": "https://player.vimeo.com/external/207496793.sd.mp4?s=c4c75c5461dcad50313f2af0258adc3c4455d4e8&profile_id=165" } ] }, { "language_id": 2, "language_name": "Hindi", "device": [ { "device_type": "tablet", "url": "https://player.vimeo.com/external/444496958.sd.mp4?s=5e2373ffcc264422c56dbb90885e98febc23f976&profile_id=165" } ] }, { "language_id": 3, "language_name": "Urdu", "device": [ { "device_type": "tablet", "url": "https://player.vimeo.com/external/641745266.sd.mp4?s=578e79074ac66e78f6b7e3d526f3db5e786fe925&profile_id=165" } ] }, { "language_id": 4, "language_name": "Polish", "device": [ { "device_type": "mobile", "url": "https://player.vimeo.com/external/641745266.sd.mp4?s=578e79074ac66e78f6b7e3d526f3db5e786fe925&profile_id=164" } ] } ] }, { "video_id": 2, "video_thumbnail": "1a9d169d6fe844543fa797ab1ac4ea0f.png", "languages": [ { "language_id": 2, "language_name": "Hindi", "device": [ { "device_type": "tablet", "url": "https://player.vimeo.com/external/641720475.sd.mp4?s=3fc5963a717f570c23bd34677be5a3f1862aa73e&profile_id=165" }, { "device_type": "mobile", "url": "https://player.vimeo.com/external/641720475.sd.mp4?s=3fc5963a717f570c23bd34677be5a3f1862aa73e&profile_id=164" } ] } ] } ] } ] }, { "session_id": 2, "session_name": "what is Diabetes", "order": 1, "steps": [ { "step_id": 1, "step_name": "Step 1", "step_type": "App\\Models\\Session\\Video", "videos": [ { "video_id": 3, "video_thumbnail": "8bba60fdb34b8369268d18379d7ee913.png", "languages": [ { "language_id": 1, "language_name": "English", "device": [ { "device_type": "tablet", "url": "https://player.vimeo.com/external/641747966.sd.mp4?s=9c5dffb95d0b93d421a2d85600951a19a5bf3aaa&profile_id=165" } ] } ] } ] } ] }, { "session_id": 3, "session_name": "Practical Skills", "order": 2 }, { "session_id": 4, "session_name": "Food & Crab Counting", "order": 3 }, { "session_id": 5, "session_name": "Food & Crab Counting 4", "order": 4 } ] } ] }
8 | http://deappdev.opapps.io/api/app-get-country | Get country list | api/app-get-country | GET |  | { "status": 1, "messages": [ "Success" ], "errors": [], "result": [ { "id": 2, "country_name": "Scotland", "country_code": "02", "status_id": 1, "weight": 200, "date": "28-Feb-2022" }, { "id": 1, "country_name": "England", "country_code": "01", "status_id": 1, "weight": 100, "date": "16-Feb-2022" } ] } | { "status": 0, "messages": [ "Error" ], "errors": [ "No country found." ] }
9 | http://deappdev.opapps.io/api/app-get-user-type | Get user type | api/app-get-user-type | GET | } | { "status": 1, "messages": [ "Success" ], "errors": [], "result": [ { "id": 3, "name": "Patient", "short_code": "P", "status_id": 1 }, { "id": 4, "name": "Guardian", "short_code": "G", "status_id": 1 }, { "id": 5, "name": "Manager", "short_code": "M", "status_id": 1 } ] } | { "status": 0, "messages": [ "Error" ], "errors": [ "No data found." ] } | Done |  | { "status": 1, "messages": [ "Success" ], "errors": [], "result": [ { "id": 3, "name": "Patient", "short_code": "P", "status_id": 1 }, { "id": 4, "name": "Guardian", "short_code": "G", "status_id": 1 }, { "id": 5, "name": "Manager", "short_code": "M", "status_id": 1 }, { "id": 6, "name": "Just Browsing", "short_code": "J", "status_id": 1 } ] }
10 | http://127.0.0.1:8000/api/get-shop-url | Get Shop url | api/get-shop-url | GET |  | { "status": 1, "messages": [ "Success" ], "errors": [], "result": [ "https://www.heal-med.co.uk/shop" ] } | { "status": 0, "messages": [ "Error" ], "errors": [ "Something went wrong try again later." ] }
11 | http://127.0.0.1:8000/api/app-change-password | Forget pasword | api/app-change-password | POST | { "deapp_id":"320P3763", "email":"roykunal1717@gmail.com" } | { "status": 1, "messages": [ "Thank you we have send a temporary password to your registered email address." ], "errors": [] } | { "status": 0, "messages": [ "Error" ], "errors": [ "Invalid deapp id !" ] }
12 | http://127.0.0.1:8000/api/app-get-session-list | session list | api/app-get-session-list | GET | { "language_id":"1", "device_type":"iPad", "deapp_id":"10001G8171" } | { "status": 1, "messages": [ "Success" ], "errors": [], "result": [ { "language_id": 1, "language_name": "English", "deapp_id": "10001G8171", "name": "asdffgdasfg", "sessions": [ { "session_id": 1, "session_name": "Introduction to the app", "order": 0, "session_show_status": 0, "steps": [ { "step_id": 1, "step_name": "Step 1", "step_type": "App\\Models\\Session\\Video", "step_type_id": 1, "step_type_thumbnail": "1a9d169d6fe844543fa797ab1ac4easc.png", "step_type_url": "https://player.vimeo.com/external/207496793.sd.mp4?s=c4c75c5461dcad50313f2af0258adc3c4455d4e8&profile_id=165", "device_type": "iPad", "step_show_status": 0 } ] }, { "session_id": 2, "session_name": "what is Diabetes", "order": 1, "session_show_status": 0, "steps": [ { "step_id": 1, "step_name": "Step 1", "step_type": "App\\Models\\Session\\Video", "step_type_id": 3, "step_type_thumbnail": "8bba60fdb34b8369268d18379d7ee913.png", "step_type_url": "https://player.vimeo.com/external/641747966.sd.mp4?s=9c5dffb95d0b93d421a2d85600951a19a5bf3aaa&profile_id=165", "device_type": "iPad", "step_show_status": 0 }, { "step_id": 2, "step_name": "2", "step_type": "App\\Models\\Session\\Video", "step_type_id": "", "step_type_thumbnail": "", "step_type_url": "", "device_type": "iPad", "step_show_status": 0 }, { "step_id": 2, "step_name": "Step 2", "step_type": "App\\Models\\Session\\Video", "step_type_id": "", "step_type_thumbnail": "", "step_type_url": "", "device_type": "iPad", "step_show_status": 0 }, { "step_id": 25, "step_name": "Step 2", "step_type": "App\\Models\\Session\\Video", "step_type_id": "", "step_type_thumbnail": "", "step_type_url": "", "device_type": "iPad", "step_show_status": 0 }, { "step_id": 25, "step_name": "Step 56", "step_type": "App\\Models\\Session\\Video", "step_type_id": "", "step_type_thumbnail": "", "step_type_url": "", "device_type": "iPad", "step_show_status": 0 } ] }, { "session_id": 3, "session_name": "Practical Skills", "order": 2, "session_show_status": 0, "steps": [] }, { "session_id": 4, "session_name": "Food & Crab Counting", "order": 3, "session_show_status": 0, "steps": [] }, { "session_id": 5, "session_name": "Food & Crab Counting 4", "order": 4, "session_show_status": 0, "steps": [] }, { "session_id": 6, "session_name": "Test_Session", "order": 5, "session_show_status": 0, "steps": [] }, { "session_id": 7, "session_name": "Test_Session1", "order": 6, "session_show_status": 0, "steps": [] }, { "session_id": 8, "session_name": "Test", "order": 10, "session_show_status": 0, "steps": [] }, { "session_id": 9, "session_name": "Test1", "order": 20, "session_show_status": 0, "steps": [] }, { "session_id": 10, "session_name": "gtftyy", "order": 21, "session_show_status": 0, "steps": [] } ] } ] }

## Test Scenario of DeApp (hidden)
Project Name | DeApp Web
Client
Reference Documnet
Created By | Indrajit Chakraborty
Creation Date | 2022-03-22
Approve Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 | None | Validate the working of Login Functionality in DeApp
TS_002 | None | Validate the wotking of Registration Functionality in DeApp
TS_003 | None | Valiadate the Profile Functionality in DeApp
TS_004 | None | Validate the Update Profile Functiobality in DeApp
TS_005 | None | Validate the Reset Password Functionality in DeApp
TS_006 | None | Validate the working of Hospital Functionality in DeApp
TS_007 | None | Validate the working of Region Functionality in DeApp
TS_008 | None | Validate the Wporking of Language Functionality in DeApp

## TestCases of DeApp (hidden)
Module Name | Test Scenario ID | Test Type | Test Case ID | Test Case Title | Pre-requisites | Test Steps | Expected Result | Actual Result | Priority | Result | Comments
Registration | TS_001 | GUI | TC_001 | Validate GUI of the Registration Page | 1) Open the DeApp Application. 2) Click on Create an Account. | 1) Checking the Title which display in Registration Page . 2) Check the spelling of the all fields. 3) Check the allignment of all the fields , text and buttons 4) Check the font of all the fields and text 5) Check the color of all the fields . 6) Check the look and feel of the page.
Registration | TS_001 | +VE | TC_002 | Validate the Registration with all valid credentials. | 1) Open the DeApp Application. 2) Click on Create an Account. | 1) Write the Name in Full Name text field. 2) Write the valid Email ID in Email text field. 3) Write the valid Password in the Password Text field. 4) Write the valid Confirm password in Confirm Password Text Field. 5) Click on Tearms & Condition check box. 6) Click on Get Started Button to register. | After write all valid credentials Click on Get Started Button To register and one message shoud be display for successfully registered and for admin approval | Application Works as expected but only After click on Get Started in Confirmation box Registed Spelling will mistake | Medium | Fail
Registration | TS_001 | -VE | TS_003 | Validate the Registration without credentials. | 1) Open the DeApp Application. 2) Click on Create an Account. | 1) Blank all the Field in Registration page Required. 2) Click on Check Box of Terms & Condition . 3) Click on Get Started Button to Register. | After Click on Get Started Button for Register as a user without all credentials User not Register and Message Should be display that Name is Required. | Application works as expected. | Hign | Pass
Registration | TS_001 | -VE | TS_004 | Validate the Registration without Name. | 1) Open the DeApp Application. 2) Click on Create an Account. | 1)Blank the Full name Text Field . 2) Write the valid Email ID in Email text field. 3) Write the valid Password in the Password Text field. 4) Write the valid Confirm password in Confirm Password Text Field. 5) Click on Tearms & Condition check box. 6) Click on Get Started Button to register. | After Click on Get Started Button for Register as a user without Name and Message Should be display that Name is Required. | Application works as expected. | Medium | Pass
Registration | TS_001 | -VE | TS_005 | Validate the Registration without Email | 1) Open the DeApp Application. 2) Click on Create an Account. | 1)Write the Full name Text Field . 2) Blank the valid Email ID in Email text field. 3) Write the valid Password in the Password Text field. 4) Write the valid Confirm password in Confirm Password Text Field. 5) Click on Tearms & Condition check box. 6) Click on Get Started Button to register. | After Click on Get Started Button for Register as a user without Email and Message Should be display that Email is Required. | Application works as expected. | Medium | Pass
Registration | TS_001 | -VE | TS_006 | Validate the Registration without Password | 1) Open the DeApp Application. 2) Click on Create an Account. | 1)Write the Full name Text Field . 2) Write the valid Email ID in Email text field. 3) Blank the valid Password in the Password Text field. 4) Write the valid Confirm password in Confirm Password Text Field. 5) Click on Tearms & Condition check box. 6) Click on Get Started Button to register. | After Click on Get Started Button for Register as a user without Password and Message Should be display that Password is Required. | Application works as expected. | Medium | Pass
Registration | TS_001 | -VE | TS_007 | Validate the Registration without Confirm Password | 1) Open the DeApp Application. 2) Click on Create an Account. | 1)Write the Full name Text Field . 2) Write the valid Email ID in Email text field. 3) Write the valid Password in the Password Text field. 4) Blank the valid Confirm password in Confirm Password Text Field. 5) Click on Tearms & Condition check box. 6) Click on Get Started Button to register. | After Click on Get Started Button for Register as a user without Confirm Password and Message Should be display that Confirm Password Required | Application Works as expected but only After click on Get Started without Comfirm Password it will display Cinfirm Is Required. | Medium | Fail
Registration | TS_001 | -VE | TS_008 | Validate the Registration without click on Terms & Condition Check Box | 1) Open the DeApp Application. 2) Click on Create an Account. | 1)Write the Full name Text Field . 2) Write the valid Email ID in Email text field. 3) Write the valid Password in the Password Text field. 4) Write the valid Confirm password in Confirm Password Text Field. 5) Without Click on Tearms & Condition check box. | After fill all credentials without click on Terms & Condition Get Started button should be not clickable. | Application works as expected. | High | Pass
Registration | TS_001 | -VE | TS_009 | Validate the Registration without proper format of Email Address | 1) Open the DeApp Application. 2) Click on Create an Account. | 1)Write the Full name Text Field . 2) Write the Email ID in Email text field withot proper format. 3) Write the valid Password in the Password Text field. 4) Write the valid Confirm password in Confirm Password Text Field. 5) Without Click on Tearms & Condition check box. | After Click on Get Started Button for Register without proper format of email and Message Should be display that Email Format Not Valid | Application works as expected. | Medium | Pass
Registration | TS_001 | -VE | TS_009 | Validate the Password and Confirm password validation in Registration | 1) Open the DeApp Application. 2) Click on Create an Account. | 1)Write the Full name Text Field . 2) Write the valid Email ID in Email text field. 3) Write the valid Password in the Password Text field. 4) Write the Confirm password but not same as Password Text Field. 5) Click on Tearms & Condition check box. 6) Click on Get Started Button to register. | After Click on Get Started Button for Register without same comfirm password as password and Message Should Confirm password not match | Application works as expected. | Medium | Pass
Registration | TS_001 | -VE | TS_009 | Validate the Password and Confirm password with minimum length allowed | 1) Open the DeApp Application. 2) Click on Create an Account. | 1)Write the Full name Text Field . 2) Write the valid Email ID in Email text field. 3) Write the 5 digit or chracter Password in the Password Text field. 4) Write the Confirm password same as Password in Confirm Password Text Field. 5) Click on Tearms & Condition check box. 6) Click on Get Started Button to register. | After Click on Get Started Button for Register without 6 digit o character password it should be show the message Password must be 6 character and not able to register | Application works as expected. | High | Pass
Login | TS_002 | +VE | TS_010 | Validate Login With Valid Credentials | 1) Open the DeApp Application. 2) Click on Create an Account. 3) Registered as a user in this Appliaction. 4) After Registerd Approve By Admin | 1) Write Valid Email for Login which provide during Registration. 2) Write Valid Password For Login which profide during Registration . 3) Click On Login Button for Login into the aplication | After write all valid credentials for login then Click on Login Button and Login Should be Succesfull and it Redirect into the Dashboard page of the aplication | Application works as expected. | High | Pass
Login | TS_002 | -VE | TS_011 | Validate Login with incorrect Email and Password | 1) Open the DeApp Application. 2) Click on Create an Account. 3) Registered as a user in this Appliaction. 4) After Registerd Approve By Admin | 1) Write incorrect Email for Login which will not provide during Registration. 2) Write incorrect Password For Login which will not provide during Registration . 3) Click On Login Button for Login into the aplication | After write all incorrect credentials for login then Click on Login Button and Login Should not be Succesfull and it not Redirect into the Dashboard page of the aplication and show message that No account found for your login attempt! | Application works as expected. | High | Pass
Login | TS_002 | -VE | TS_012 | Validate Login without Email | 1) Open the DeApp Application. 2) Click on Create an Account. 3) Registered as a user in this Appliaction. 4) After Registerd Approve By Admin | 1) Write without Email for Login which will provide during Registration. 2) Write valid Password For Login which will provide during Registration . 3) Click On Login Button for Login into the aplication | After click on Login without Email it should be show message that Email is required . | Application works as expected. | High | Pass
Login | TS_002 | -VE | TS_013 | Validate Login without Password | 1) Open the DeApp Application. 2) Click on Create an Account. 3) Registered as a user in this Appliaction. 4) After Registerd Approve By Admin | 1) Write valid Email for Login which will provide during Registration. 2) Write without Password For Login which will provide during Registration . 3) Click On Login Button for Login into the aplication | After click on Login without Password it should be show message that Password is required. . | Application works as expected. | High | Pass
Login | TS_002 | -VE | TS_014 | Validate Login with valid Email but incorrect Password | 1) Open the DeApp Application. 2) Click on Create an Account. 3) Registered as a user in this Appliaction. 4) After Registerd Approve By Admin | 1) Write valid Email for Login which will provide during Registration. 2) Write incorrect Password For Login which will not provide during Registration . 3) Click On Login Button for Login into the aplication | After click on Login with incorrect Password but valid Email ID it should be show message that Password is Incorrect. | Application works as expected. | High | Pass
Login | TS_002 | -VE | TS_015 | Validate Login with incorrect Email but correct Password | 1) Open the DeApp Application. 2) Click on Create an Account. 3) Registered as a user in this Appliaction. 4) After Registerd Approve By Admin | 1) Write incorrect Email for Login which will not provide during Registration. 2) Write valid Password For Login which will provide during Registration . 3) Click On Login Button for Login into the aplication | After click on Login with correct Password but incorrect Email ID it should be show message that No account found for your login attempt! | Application works as expected. | High | Pass
Login | TS_002 | -VE | TS_015 | Validate Login with Valid Email and Password but not apporved by the admin after Registration | 1) Open the DeApp Application. 2) Click on Create an Account. 3) Registered as a user in this Appliaction. 4) After Registerd Approve By Admin | 1) Write correct Email for Login which will provide during Registration. 2) Write valid Password For Login which will provide during Registration . 3) Click On Login Button for Login into the aplication | After click on Login with correct Password and correct Email ID but not approved by admin it should be show message that Your account is not verified yet please wait for admin approval. | Application works as expected. | High | Pass
Profile | TS_003 | GUI | TS_016 | Validate the GUI and data after click on Profile. | 1) Open the DeApp Application. 2) Click on Create an Account. 3) Registered as a user in this Appliaction. 4) After Registerd Approve By Admin 5) Login With Credentials. | 1) Click on write side top Image logo. 2) Click on Proile. 3) After Click on Profile Validate all the Data in Profile page according with the Registration. 4) Check the spelling of the all fields. 5) Check the allignment of all the fields , text and buttons 6) Check the font of all the fields and text 7) Check the color of all the fields . 8) Check the look and feel of the page. | Application should maintain tis consistancy | Application works as expecetd | High | Pass
Update Profile | TS_004 | +VE | TS_017 | Validate the Update Profile after Login. | 1) Open the DeApp Application. 2) Click on Create an Account. 3) Registered as a user in this Appliaction. 4) After Registerd Approve By Admin 5) Login With Credentials. | 1) Clik on Profile . 2) Clik on Profile Update. 3) Edit the Profile name from previous one . 4) Click on Update Button to update. 5) After Clik on Update Check Mesage Show that Profile Successfully Update. 6) After Update Profile name check that this update profile name display on Profile page. 7) Again Click onUpdate Profile button for Image Upload. 8) Clik on Upload Picture and choose the image from device and Clik on Update Button to upload Image . 9) After Clik on Update Button It show Message that Profile Succesfully Updated but No image will upload and not show image in Profile page | Application should maintain tis consistancy . | Application works as expected but Image Not uploaded Succesfully | Medium | Pass
Update Profile | TS_004 | -VE | TS_018 | Validate the Update Profile Name With Single Character. | 1) Open the DeApp Application. 2) Click on Create an Account. 3) Registered as a user in this Appliaction. 4) After Registerd Approve By Admin 5) Login With Credentials. | 1) Clik on Profile . 2) Clik on Profile Update. 3) Write The Single Charcter of the Name . 4) Click on Update Button to update. | Profie name should not be Updated and show the Message Enter atleasr three character . | Application is works as expecetd but after clik o save button refresh the page some data will remove from Profile list. | High | Fail
Update Profile | TS_004 | -VE | TS_019 | Validate Update Profile Name Without Click on Upodate Button | 1) Open the DeApp Application. 2) Click on Create an Account. 3) Registered as a user in this Appliaction. 4) After Registerd Approve By Admin 5) Login With Credentials. | 1) Clik on Profile . 2) Clik on Profile Update. 3) Write the updated Name in the Profile Update Name Filed. 4) Click on Close Button instead of Update button. | Profile Name Should not be Update. | Application is works as expected but and Name will not Update but after again go the Profile update and Previous Update name that entered for Updae will show . | Medium | Fail
Reset Password | TS_005 | GUI | TS_020 | Validate the GUI of the Reset Password Page. | 1) Open the DeApp Application. 2) Click on Create an Account. 3) Registered as a user in this Appliaction. 4) After Registerd Approve By Admin 5) Login With Credentials. 6) Go to the Profile . | 1) Checking the Title which display in Reset Password Page . 2) Check the spelling of the all fields. 3) Check the allignment of all the fields , text and buttons 4) Check the font of all the fields and text . 5) Check the color of all the fields . 6) Check the look and feel of the page. | Application Should maintain this consistancy. | Application is works as expecetd. | Medium | Pass
Reset Password | TS_005 | +VE | TS_021 | Validate the Reset Password will valid credentials | 1) Open the DeApp Application. 2) Click on Create an Account. 3) Registered as a user in this Appliaction. 4) After Registerd Approve By Admin 5) Login With Credentials. 6) Go to the Profile . | 1) Click on Reset Password Button and go to Reset Password page. 2) Write The Old Password in the Old Password Text Field. 3) Write the New Password that to be change in the Password field. 4) Write the Confirm Password in the Confirm Password text field. 5) Click on Updae Button to Update the Password. 6) Check that after Clik on update Message will show that Password change succesfully. | Application Should maintain this consistancy. | Application is works as expected. | High | Pass
Reset Password | TS_005 | -VE | TS_022 | Validate the Reset Password will some Negative Test | 1) Open the DeApp Application. 2) Click on Create an Account. 3) Registered as a user in this Appliaction. 4) After Registerd Approve By Admin 5) Login With Credentials. 6) Go to the Profile . | 1) Click and go to the Reset Password page. 2) Write Altenately data in all Reset Password field and check the proper message display or not. | Application Should maintain this consistancy. | Application is works as expected. | High | Pass

## Bug Report for DeApp (hidden)
Sl No. | Module Name | Bugs Description | Screenshot | Severity | Priority | Reported By | Assign To | Status | Put Tick If Bug Fix (For Developer) | Put Tick If Bug Fix (For Tester) | Notes | Comments(dev)
1 | Registration | Issue in After Registration Message spelling Mistake. |  |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
2 | Registration | In Registration Full Name Field If i enter any name with Single Character it will show that Message Please Enter Your Name But Successfully Registered i think there should be some validation of minimum character. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
3 | Registration | In Registration when email domain outlook.com and yahoo.com use it show invalid Email Format But for Rediff.com and hotmail.com it will take and successfully registered. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
4 | Registration | After blank Confirm Password field register message show that Confirm is required but i think it should be show Confirm Password Required instead of Confirm Required. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
5 | Profile Update | In Edit Profile Name Filed must be at list 3 character not takes any single character. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
6 | Profile Update | In Update Profile When Upadte name and after Click it will sucessfully update and dispaly the updated Name but when Refresh the page after update some Data like Joint At , User Role and Email will remove. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Accept | FALSE | FALSE
7 | Profile Update | In Profile when Edit existing name but not click on Save , click Close and then again Click on Profile Update it will take the old update name that we entered for update. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
8 | Reset Password | In Forget Password when left blank the confirm password field it will show message that confirm is required instead of Confirm Passwprd is required. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
8 | Reset Password | In Forget Password when Old password not porperly wite it will and click other Password and Cnf Password fill and update the message will show Current password does not match i think there should be Old Password Does not match | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
9 | Reset Password | When fill Password and Cnf Password but Old password field left blank it will show Something went wrong error messsage | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
10 | Reset Password | When left the Cnf password field left it will show message Confirm is required instead Confirm Password is Required. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
11 | Reset Password | When make the Old Password mismatch and reset it will show Current password is not match instead of Old Password is not match . | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
12 | Forget Password In Login Screen | When Click on Forget Password It will show lodaing continuous loding. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Accept | FALSE | FALSE
13 | Country | In Add Country left Reagion Name and Code Field and click on Save It will show the Message label is Required but there should be show Name is required instead of label. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
14 | Country | In Add Country add country name and code and after save when and then Clik on view or edit the the code will not show which provide earliar during add Country. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
15 | Country | Suppose Two region are added 1) TEST 2) Test it not takes . i think there should be added because name are same both are different in Case sensitive | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE | Its Not A bug
16 | Language | In Language delete all Existing Language and after refresh the page it show some message that something wents wrong | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
17 | Hospital | Issue In Hopial Country Dropdown when Edit it show doubble Country of same name. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
18 | Hospital | After Inactive the status os Hospital and then Update the hospital details and after save inactive also updated as active. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
19 | Hospital | In Add New Hospital Weight field is not mandetory but in update it how weight field is mandetory. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
20 | Hospital | When add new hospital with pz code and edit hosptal any details and click on Update it will show message Pz code already taken | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
21 | Hospital | In Hospital name it takes Single Character only. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
22 | Hospital | In Hospital Add without fill the Country name and save it will show Region name instead of Country name. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
23 | Hospital | After Delete All Hospital and refresh the same page No data found message will display. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
24 | User | In add Patient when All field are left blank and click on Add Button it show Region is Required but there Region Field is not preasent | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
25 | User | When Add patient without Country Name and go to edit and chilk on Update It show Region is Required. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
26 | User | Click on User then Show message that no data found but i have old User data. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
27 | User | Delete Not Working in User List | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
28 | User | After Delete User No Confirmation Delete Message will dsplay and user no ditails not display but when refresh the page this delete user again show. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
29 | User | When Update User With Country Which Hospital Was Inactive when choose this country and clik on Hospital list dropdown it will show empty but when clik ouside the same inactive hospital will show. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
30 | User | When Select Country with Hospital in Admin User and User it will select Successfully but if i Deselect Country Hospital Name will auto remove from Hospital dropdown. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Accept | FALSE | FALSE
31 | Hospital Admin | If I inactive hospital and then go to add hopital admin and edit some admin with this Country which hospital was inactive and Hospital name Not Automaticaaly Remove So that Whn Click Update It will update Successfully. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
32 | Manage User | After In Active User then open this user with same credentials the successfully log in .There should be not able to login when user inactive. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
33 | Manage User | When Change the Country in Edit User then save and after that go to edit again this country name not show it will show different country name. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Complete | TRUE | TRUE
34 | DeApp | When Open Any Module in Deapp like Hospital , language etc in Tab Heading will mismath according with the Module name that open currently. | Not Availabe |  |  | Indrajit Chakraborty | Santanu Tung and Sagar Masanta | Open | FALSE | FALSE
| Notes : Need To be Implement In DeApp | 1) Loader Add in deapp dev after click any module . 2) n language Country after write details and press enter it must be save 3) In Password field i think there some show option will be available than can user easyly see what password he entered.

## App_Api Test Report (hidden)
Tc_Id | Title | Request URL | HTTP Method (GET/POST/PUT/DELETE) | Request Body | Auth Keys | Response | Validations | Result | Bugs | Status | Accept Date | Complete Date | Note
TC_001 | Test and Validate New User Register API | http://deappdev.opapps.io/api/app-register | POST | { "name":"Indrajit Chakraborty", "email":"indrajit.chakraborty@onepatch.com", "user_type":"1", "country_id":"1", "hospital_id":"3", "password":"123456", "password_confirmation":"123456" } | NA | { "status":1, "messages":[ "You have successfully resgistered." ], "errors":[ ], "result":[ { "id":31, "name":"Indrajit Chakraborty", "deapp_id":"10101P8337", "email":"indrajit.chkraborty@onepatch.com", "date":"17-Mar-2022" } ] } | Response Bode , Status Code --> 200 Content Type --> application/json Response Time --> 3.0 sec | Pass |  | Complete
TC_002 | Test and Validate New User Register API Without Name | http://deappdev.opapps.io/api/app-register | POST | { "name":" ", "email":"indrajit.chakraborty@onepatch.com", "user_type":"1", "country_id":"1", "hospital_id":"3", "password":"123456", "password_confirmation":"123456" } |  | { "status":0, "messages":"Error", "errors":[ "The name field is required." ] } | Response Bode Status Code --> 200 Content Type --> application/json Response Time --> 8.0 sec | Fail | Error Message are not in Array | Accept |  |  | Updated on dev no yeat in live
TC_003 | Test and Validate New User Register API Without Email | http://deappdev.opapps.io/api/app-register | POST | { "name":" Indrajit Chakraborty", "email":" ", "user_type":"1", "country_id":"1", "hospital_id":"3", "password":"123456", "password_confirmation":"123456" } |  | {"status":0,"messages":"Error","errors":["The email field is required."]} | Response Bode Status Code --> 200 Content Type --> application/json Response Time --> 4.0 sec | Fail | Error Message are not in Array | Accept |  |  | Updated on dev no yeat in live
TC_004 | Test and Validate New User Register API without Email & Password | http://deappdev.opapps.io/api/app-register | POST | { "name":" ", "email":" ", "user_type":"1", "country_id":"1", "hospital_id":"3", "password":"123456", "password_confirmation":"123456" } |  | {"status":0,"messages":"Error","errors":["The email field is required.","The password field is required."]} | Response Bode Status Code --> 200 Content Type --> application/json Response Time --> 4.0 sec | Fail | Error Message are not in Array | Accept |  |  | Updated on dev no yet in live
TC_005 | Test and Validate New User Register API with same email and without Password match Confirmation | http://deappdev.opapps.io/api/app-register | POST | { "name":"ndrajit Chakraborty", "email":" indrajit.chakraborty@onepatch.com", "user_type":"1", "country_id":"1", "hospital_id":"3", "password":"123456", "password_confirmation":"12345" } |  | {"status":0,"messages":"Error","errors":["The email has already been taken.","The password confirmation does not match."]} | Response Bode Status Code --> 200 Content Type --> application/json Response Time --> 4.0 sec | Fail | Error Message are not in Array | Accept |  |  | Updated on dev no yet in live
TC_006 | Test and Validate New User Register API with existing credentials | http://deappdev.opapps.io/api/app-register | POST | { "name":"Indrajit Chakraborty", "email":"indrajit.chakraborty@onepatch.com", "user_type":"1", "country_id":"1", "hospital_id":"3", "password":"123456", "password_confirmation":"123456" } |  | {"status":0,"messages":"Error","errors":["The email has already been taken."]} | Response Bode Status Code --> 200 Content Type --> application/json Response Time --> 4.0 sec | Fail | Error Message are not in Array | Accept |  |  | Updated on dev no yet in live
TC_007 | Test and Validate Login API with valid credentials | http://deappdev.opapps.io/api/app-login | POST | { "username":"indrajit.chakraborty@onepatch.com", "password":"123456" } |  | {"status":1,"messages":["You have login successfully."],"errors":[],"result":[{"id":31,"name":"Indrajit Chakraborty","email":"indrajit.chkraborty@onepatch.com","date":"17-Mar-2022","token":"145¦tPf6W8HH34nTkMIoyoFxQ0QhlpIy2pFL2nro2xFZ"}]} | Response Body Status Code --> 200 Content Type --> application/json Response Time --> 2.0 sec | Pass |  | Complete
TC_008 | Test and Validate Login API with incorrct username | http://deappdev.opapps.io/api/app-login | POST | { "username":"indrajit.chakraborty1@onepatch.com", "password":"123456" } |  | {"status":0,"messages":["Error"],"errors":["IWrong email or username, please check it and enter again!"]} | Response Body Status Code --> 200 Content Type --> application/json Response Time --> 3.0 sec | Pass |  | Complete
TC_009 | Test and validate Login API with Incorrect Password | http://deappdev.opapps.io/api/app-login | POST | { "username":"indrajit.chakraborty@onepatch.com", "password":"123456458" } |  | {"status":0,"messages":["Error"],"errors":["Incorrect password, please check it and enter again!"]} | Response Body Status Code --> 200 Content Type --> application/json Response Time --> 3.0 sec | Pass |  | Complete
TC_010 | Test and validate Login API without Username and Password | http://deappdev.opapps.io/api/app-login | POST | { "username":"", "password":"" } |  | {"status":0,"messages":"Error","errors":["Username can not be blank!"]} | Response Body Status Code --> 200 Content Type --> application/json Response Time --> 1.0 sec | Fail | Error Message are not in Array | Accept |  |  | Updated on dev no yet in live
TC_011 | Test and validate Quick Links API | http://deappdev.opapps.io/api/quick-links | GET |  |  | { "status":true, "messages":[ ], "errors":[ ], "sections":[ { "id":18, "value":"useful_information", "label":"Useful Information", "quick_links":[ { "id":43, "value":"sickday_rules", "label":"Sickday Rules", "url":"https:\/\/s3-.amazonaws.com\/\/618eb0c3edd7f_Patient-advice-for-sick-day.pdf", "type":{ "id":1, "value":"pdf", "label":"PDF" } }, { "id":44, "value":"glucagonglucagen-_how_to_give_an_injection", "label":"Glucagon\/Glucagen - How to give an injection", "url":"https:\/\/player.vimeo.com\/external\/207451449.sd.mp4?s=24d24db5337ecee2418822b20c4ffccbce464159&profile_id=165", "type":{ "id":3, "value":"video", "label":"Video" } }, { "id":45, "value":"healmed_website", "label":"HEAL.med website", "url":"https:\/\/www.heal-med.co.uk", "type":{ "id":2, "value":"url", "label":"URL" } }, { "id":46, "value":"ketone_sticker", "label":"Ketone Sticker", "url":"https:\/\/s3-.amazonaws.com\/\/61de6b2198fdf_Deapp-Ketone-Sticker.pdf", "type":{ "id":1, "value":"pdf", "label":"PDF" } } ] } ] } | Response Body Status Code --> 200 Content Type --> application/json Response Time --> 1.0 sec | Pass |  | Complete
TC_012 | Test and validate Get Language List | http://deappdev.opapps.io/api/app-get-language | GET |  |  | {"status":1, "messages":["Success"], "errors":[], "result":[[{"id":4,"label":"Polish","status_id":2,"date":"7-Mar-2022"}, {"id":3,"label":"Urdu","status_id":1,"date":"7-Mar-2022"}, {"id":2,"label":"Hindi","status_id":1,"date":"7-Mar-2022"}, {"id":1,"label":"English","status_id":1,"date":"7-Mar-2022"}]]} | Response Body Status Code --> 200 Content Type --> application/json Response Time --> 1.0 sec | Pass |  | Complete
TC_013 | Test and validate Get Hospitals | http://deappdev.opapps.io/api/app-get-hospitals | POST | { "region_id":1 } |  | <!DOCTYPE html> <html lang="en"> <head> <meta charset="utf-8"> <meta http-equiv="X-UA-Compatible" content="IE=edge"> <meta name="viewport" content="width=device-width, initial-scale=1, maximum-scale=1, shrink-to-fit=no"> <meta name="csrf-token" content="2dtZXdwf5HPdoOd9NA5jMVHKWP4KNTmlwfLOJ9fN"> <title>DeApp</title> <link rel="stylesheet" href="http://deappdev.opapps.io/css/app.css?id=b4de71a7cc813ef7bbcc"> <link rel="shortcut icon" href="http://deappdev.opapps.io/images/deapp-logo-1.png"> <link href="https://fonts.googleapis.com/css?family=Nunito:400,600,700" rel="stylesheet"> <!-- datatable css cdn --> <link rel="stylesheet" href="https://cdn.datatables.net/1.10.24/css/jquery.dataTables.min.css"> <!-- datatable js cdn --> </head> <body> <noscript> <strong>We're sorry but Cork doesn't work properly without JavaScript enabled. Please enable it to continue.</strong> </noscript> <div id="pageloading" class="loading">Loading&#8230;</div> <div id="app"></div> | Response Body Status Code --> 200 Content Type --> text/html; charset=UTF-8 Response Time --> 1.0 sec | Fail | Response not get in JSON Contel type will text/html; charset=UTF-8 |  |  |  | Updated on dev no yeat in live
TC_014 | Test and Validate Get Hospital Details API with valid hospital id | http://deappdev.opapps.io/api/app-get-hospitals-details | POST | { "hospital_id":"2" } |  | {"status":1,"messages":["Success"],"errors":[],"result":[{"id":2,"hospital_name":"AMRI","status_id":1,"region_id":1,"pz_code":"PZ100","region_name":"England","office_contact_weekdays":"98877665544","dietitian_contact":"98888667788","switchboard":"87777556677","email_signoff":"amri@gmail.com","weight":100,"out_of_hours_contact":"98888667890"}]} | Response Body Status Code --> 200 Content Type --> application/json Response Time --> 1.0 sec |  |  | Accept
TC_015 | Test and Validate Get Hospital Details API with incorrect hopital id | http://deappdev.opapps.io/api/app-get-hospitals-details | POST | { "hospital_id":"0" } |  | {"status":0,"messages":["Error"],"errors":["No data found !"]} | Response Body Status Code --> 200 Content Type --> application/json Response Time --> 1.0 sec | Pass |  | Complete
TC_016 | Test and Validate Get Session API | http://deappdev.opapps.io/api/app-get-sessions | GET |  |  | { "status":1, "messages":[ "Success" ], "errors":[ ], "result":[ { "sessions":[ { "session_id":1, "session_name":"Introduction to the app", "order":0, "steps":[ { "step_id":1, "step_name":"Step 1", "step_type":"App\\Models\\Session\\Video", "videos":[ { "video_id":1, "video_thumbnail":"1a9d169d6fe844543fa797ab1ac4easc.png", "languages":[ { "language_id":1, "language_name":"English", "device":[ { "device_type":"tablet", "url":"https:\/\/player.vimeo.com\/external\/207496793.sd.mp4?s=c4c75c5461dcad50313f2af0258adc3c4455d4e8&profile_id=165" } ] }, { "language_id":2, "language_name":"Hindi", "device":[ { "device_type":"tablet", "url":"https:\/\/player.vimeo.com\/external\/444496958.sd.mp4?s=5e2373ffcc264422c56dbb90885e98febc23f976&profile_id=165" } ] }, { "language_id":3, "language_name":"Urdu", "device":[ { "device_type":"tablet", "url":"https:\/\/player.vimeo.com\/external\/641745266.sd.mp4?s=578e79074ac66e78f6b7e3d526f3db5e786fe925&profile_id=165" } ] }, { "language_id":4, "language_name":"Polish", "device":[ { "device_type":"mobile", "url":"https:\/\/player.vimeo.com\/external\/641745266.sd.mp4?s=578e79074ac66e78f6b7e3d526f3db5e786fe925&profile_id=164" } ] } ] }, { "video_id":2, "video_thumbnail":"1a9d169d6fe844543fa797ab1ac4ea0f.png", "languages":[ { "language_id":2, "language_name":"Hindi", "device":[ { "device_type":"tablet", "url":"https:\/\/player.vimeo.com\/external\/641720475.sd.mp4?s=3fc5963a717f570c23bd34677be5a3f1862aa73e&profile_id=165" }, { "device_type":"mobile", "url":"https:\/\/player.vimeo.com\/external\/641720475.sd.mp4?s=3fc5963a717f570c23bd34677be5a3f1862aa73e&profile_id=164" } ] } ] } ] } ] }, { "session_id":2, "session_name":"what is Diabetes", "order":1, "steps":[ { "step_id":1, "step_name":"Step 1", "step_type":"App\\Models\\Session\\Video", "videos":[ { "video_id":3, "video_thumbnail":"8bba60fdb34b8369268d18379d7ee913.png", "languages":[ { "language_id":1, "language_name":"English", "device":[ { "device_type":"tablet", "url":"https:\/\/player.vimeo.com\/external\/641747966.sd.mp4?s=9c5dffb95d0b93d421a2d85600951a19a5bf3aaa&profile_id=165" } ] } ] } ] } ] }, { "session_id":3, "session_name":"Practical Skills", "order":2 }, { "session_id":4, "session_name":"Food & Crab Counting", "order":3 }, { "session_id":5, "session_name":"Food & Crab Counting 4", "order":4 } ] } ] } | Response Body Status Code --> 200 Content Type --> application/json Response Time --> 1.0 sec | Pass |  | Complete
TC_017 | Test and Validate Get Country List API | http://deappdev.opapps.io/api/app-get-country | GET |  |  | {"status":1,"messages":["Success"],"errors":[],"result":[[{"id":2,"country_name":"North East","country_code":"02","status_id":1,"weight":200,"date":"28-Feb-2022"},{"id":1,"country_name":"England","country_code":"01","status_id":1,"weight":100,"date":"16-Feb-2022"}]]} | Response Body Status Code --> 200 Content Type --> application/json Response Time --> 1.0 sec |  |  | Complete
TC_018 | Test and Validate Get User Type API | http://deappdev.opapps.io/api/app-get-user-type | GET |  |  | {"status":1,"messages":["Success"],"errors":[],"result":[[{"id":1,"user_type_name":"Patient","user_type_code":"P","status_id":1},{"id":2,"user_type_name":"Guardian","user_type_code":"G","status_id":1},{"id":3,"user_type_name":"Manager","user_type_code":"M","status_id":1},{"id":4,"user_type_name":"Admin","user_type_code":"A","status_id":1},{"id":5,"user_type_name":"Just Browsing","user_type_code":"J","status_id":1}]]} | Response Body Status Code --> 200 Content Type --> application/json Response Time --> 1.0 sec | Pass |  | Complete